Timeline: 2022-2025 Transitions Strategic Plan

|  |  |  |
| --- | --- | --- |
| **ITEM** | **COMPLETION DATE** | **RESPONSIBLE** |
| 1. Review Results of Board Satisfaction Survey
 | 10/31/21 | Governance Committee, BoD (October meeting) |
| 1. Review current Strategic Plan (SP), determine on-going items, finalize questions for interviews
 | 10/31/21 | Governance Committee, Transitions management |
| 1. Conduct surveys (not anonymous)
2. BoD
3. Board Committees – any goals to accomplish over next 3 years
4. Staff
5. Transitions Management
6. Key Community Members
 | 12/31/21 – 3/31/21 | 1. completed
2. Committee Chairs
3. Heather Over
4. Mae Ling
5. Governance Committee members, Mae-Ling
 |
| 1. Submit List of Key Stakeholders to Tracy Strosser
 | 2/9/22 | Governance Committee, Transitions Membership |
| 1. Tracy will email committee Stakeholder Assignments
 | 2/11/22 | Tracy Strosser |
| 1. Complete Key Stakeholder Interviews
2. Transitions Employees/Departments will complete programmatic SWOTs
 | 3/14/22 | Governance CommitteeTransitions Leadership & Staff |
| 1. Key Stakeholder Interviews are entered into Survey Monkey
 | 3/21/22 | Governance CommitteeMae-Ling and Delegated Employees |
| 1. Present draft SP to staff for review and comment
 | April BoD meeting | Mae-Ling |
| 1. Present draft SP to BoD for review and comment
 | April BoD meeting | Mae-Ling & Governance Chair |
| 1. Finalize Draft SP for final review of the BoD
 | May BoD meeting | Mae-Ling & Governance Chair |
| 1. Approve final SP
 | June BoD meeting | Governance Committee, BoD |